## product backlog
Product Backlog Id | Priority | User Story Id | User story | Scrum team assign | Status | Remark
1 | High | User001 | User Registration | Hitesh | Complete | NA
2 | Low | User002 | Notification | Kumar jd | Not Started | 1 Hour dealy
3 | Low | User003 | Cart | Jaswanth | Progress | NA
4 | Medium | User004 | Reset Password | Apurva Shinde | Complete | NA
5 | High | User005 | Hotel Search | Amar Kolhe | Complete | NA
6 | High | User006 | Payment | Anusha Bharath | Complete | NA
7 | Medium | User007 | Address mgmt | Bhavani | Progress | NA
8 | High | User008 | Rewards | Atin | Complete | NA
9 | High | User009 | Photographs | Ashish | Progress | Wating for Photos
10 | Medium | User010 | Reviews | Aravind Naidu | Progress | NA
11 | High | User011 | User Login | Dipti | Complete | NA

## sprint backlog 1
User story id | User story name | User story step defination | Assigned to | Estimated time | Actual time | Acceptance Criteria | Status | Remarks
User001 | User Registration | As a user I can provide my email id, phone no., password, username, gender, DOB for registration After successful registration as a user I am navigated to the home screen | Hitesh | 3 hours | 3 hours | Search results include hotels matching the destination | Complete | NA
User005 | Hotel Search | As a Traveler, I want to Select the catagories . | Amar kolhe | 5 hour | 3 hour |  | Complete | NA
User006 | Payment | As a Traveler, I want to Select the date. | Anusha Bharath | 1 hour | 1 hour |  | Complete | NA

## sprint backlog 2
User story id User story name User story step defination Assigned to Estimated time Actual time Acceptance Criteria Status Remarks
User002 | Notification | As a Traveler, I want to find available options for my hotel | Kumar jd | 1 hour | 1 hour | Filters allow narrowing results by price, rating, amenities | Not started | 1 Hour delay
User003 | Cart | As a Traveler , I want to view detailed information about each hotel, | Jaswanth | 4 hour | 4 hour | display key information like hotel name, photos, price, | Progress | NA
User004 | Reset Password | As a Traveler, I want to view including photos, amenities, and reviews | Apurva shinde | 7 hour | 4 hour |  | Complete | NA

## sprint backlog 3
User story id | User story name | User story step defination | Assigned to | Estimated time | Actual time | Acceptance Criteria | Status | Remarks
User007 | Address mgmt | As a Traveler, I want to book the room. | Bhavani | 4 hour | 3 hour |  | Progress | NA
User008 | Rewards | As a Traveler, I want to payment option. | Atin | 5 hour | 4 hour |  | Complete | NA
User009 | Photographs | As a Traveler, I want to notify about booking . | Ashish | 4 hour | 3 hour |  | Progress | Waiting for photos
User010 | Reviews | As a Traveler, I want to confirm my room booking. | Aravind Naidu | 3 hour | 2 hour |  | Progress | NA
User011 | User Login | As a Traveler, I want to logout . |  | 3 hour | 2 hour |  | Complete | NA

## Kanban
TODO | In Progress |  |  |  |  | Completed
|  | Design | Develop | Test | Deploy
User story | done | done | done | done | done | Complete
User Registration | done | done | done | done | done | Complete
Notification | done | done | done |  | done | Complete
Cart | done | done | done | done | done
Reset Password | done | done | done | done | done | Complete
Hotel Search | done | done | done | done | done | Complete
Payment | done | done |  | done | done | Complete
Address mgmt | done | done | done | done | done | Complete
Rewards | done | done | done | done | done | complete
Photographs | done | done | done |  | done | Complete
Reviews | done | done | done |  | done
User Login | done | done | done | done | done | Complete

## Defact Tracking
Defect id | Defect | Created On | Creater | Assign to | Serverity | priority | status
doo1 | Login Function is not Working | 2024-06-18 | Aravind Naidu | Dipti | medium | high | close
doo2 | Can not able to search hotel by neaarby location | 2024-06-19 | Apurva Shinde | Amar Kolhe | high | medium | close
doo3 | User is not able to pay with the debit card | 2024-06-19 | Hitesh | Anusha Bharath | medium | low | open
doo4 | Issue in selecting the category | 2024-06-20 | Ashish | Jaswanth | low | high | close
doo5 | Address is wrong | 2024-06-20 | Kumar jd | Bhavani | medium | low | open